## Sheet1
Scope
Manual Exploratory testing and Usability testing will be performed

Goals
Application under test has five main areas as shown on the below mindmap:

Test Team has assigned the following levels of their importance for each area:
	Area	Importance
	Booking management	Critical
	Profile	High
	Tours	Critical
	Search	Low
	Chat	Medium

As there are no business requirements defined testers will perform exploratory testing with main focus on system stability and usability on each of those areas. / The goal is to create Test Cases, Defect report and Usability enhancements for those areas.

Out of scope
Performance testing, Security testing is out of scope. Automation testing is out of scope as only one iteration is planned.

Assumptions
Web application is up and running. Testers are able to access application via https://www.phptravels.net/supplier
Each application area is operational.

Schedule
Schedule for all testing activities: Start 17 June 2018. End: 15 July 2018
Further schedule break down:
	Bookind management: start: 17 June 2018 end
	Profile: start: end
	Tours: start: end
	Search: start: end
	Chat: start: end

Roles and Responsibilities
M-Team is responsible for executing exploratory and usability testing, creating test cases and defect reports.
M-Team members: Monika, Ewa, Mariusz, Maciej
Robert and Bartek are Business Owners, L1 support, coacher for testers.

Deliverables
Mindmap with functional architecture of application under test.
Test Cases and Defects report created during testing activities.
Usability enhancements.
Test Report with the following statistics:
	Total number of TestCases
	NoRun TestCaes

	Total number of Defects
	Open Defects